## Action Tracker
title | task_id | owner | Status | Start Date | ETA | description | last_updated
Prepare complete demo aligned to lifeblood email |  | Sridhar / Sanjay | in process |  |  | Ensure all required components are covered
Develop demo scenario (end-to-end flow) |  | Raj / Sanjay | in process |  |  | Simple app flow for migration demo
Create reusable demo script/video(python SDK /Terraform/ShellScript) |  | Team | in process |  |  | Reusable execution
Ensure VPC landing zone demo readiness |  | Santhosh | in process |  |  | Validate IAC creation
Restructure questionnaire with sections |  | Sanjay | in process |  |  | Organize into logical sections
Add 'What we know' sheet. |  | Team | Not Started |  |  | Capture assumptions
Convert questions to validation format |  | Sanjay | in process |  |  | Show prior understanding
Finalize and share questionnaire |  | Team | in process |  |  | Send to stakeholders
Complete and clean network diagram |  | Santhosh | Done |  |  | Remove assumptions
Add missing components to diagram |  | Santhosh | Done |  |  | Include DBs, on-prem, flows
Differentiate Classic vs VPC visually |  | Santhosh | Done |  |  | Use color coding
Include all regions in diagram |  | Santhosh | Not Started |  |  | Frankfurt, London, Sydney
Validate diagram with stakeholders |  | Sridhar | Not Started |  |  | Check with Balaji/IBM
Follow up on pending inputs |  | Sridhar | Not Started |  |  | Balaji & John
Get required access (Slack etc.) |  | Team | done |  |  | Enable communication
Resolve Viata access/setup delay |  | Sridhar / Santhosh | in process |  |  | Coordinate with Santosh C
Import & interpret firewall rules |  | Santhosh | Not Started |  |  | Use Viata
Prepare initial slide deck |  | Raj | in process |  |  | 10-15 slides
Add migration examples to slides |  | Raman / Raj | Not Started |  |  | Enhance storytelling
Build environment inventory |  | Team | Not Started |  |  | Servers, VLANs, apps
Map traffic flow |  | Sanjay | in process |  |  | End-to-end architecture
Validate region types (MZR/SZR) |  | Raj | Done |  |  | Check VPC feasibility
Align team on priorities |  | Team | Not Started |  |  | Demo vs long-term
Escalate blockers when needed |  | Sridhar | Not Started |  |  | Use escalation support
Add Customer Question: we don't see DXN Vayatta configuration.
Need a slides for 5 b section
5 b vii need a slide explaining the how and what configure we are going to use for the landing zone
Santhosh: make sure the picture has exactly same information as we have in asset inventory |  | Santosh | DOne
Baremetal Virtualization setup |  | Parikshit | Done |  |  | Cretaed Baremetal with windows server 2022 with 2 VMs
Setup environment qemu-image for qcow2 convert |  | Parikshit | Done |  |  | converted VHDX to qcow2 using qemu-img
Automated the dicovery on VM image within hyperv using jump enviornmenmt |  | Parikshit | Done |  |  | Disovered the VM inventory (Name , CPU, Memory , Drive space, VHDX path) and exported to csv
Inatalled the VMvare Esxi 6.7 on baremetal to simulate VMDK to qcow2 and automation |  | Parikshit | Inprogress |  |  | installation done public IP configuratio is in progress
windows simulation with RMM tool |  | Parikshit | Inprogress |  |  | coordinating with Rackware team
capture the error and bugs of RMM and documentation |  | Parikshit | Inprogress |  |  | Prepared excel sheet and continue adding P
Openshift cluster instalation and import qcow2 images |  | Parikshit | Inprogress |  |  | preparing to deploye cluster
Windows host migration with new user having "infobell" name |  | Parikshit | Done | 27/4/2026 | 27/4/2026 | able to login with infobell user but not with administrator. mail sent to rackware team